## Slide 1: Rotary Zone 8
Regionalisation
Year by Year

## Slide 2: The Vote September 22
YES
We want to explore, test and develop
OR
NO
We want to stay the same

## Slide 3: Governance

## Slide 4: How did it happen?
2018 -2019 Governors got talking
They sent a petition to RI
The petition sought approval to develop a coordinated regional approach to brand awareness, declining membership, community partnerships, fundraising, and change management in order to better support clubs.

## Slide 5: Who’s who in the Zoo? The Zone 8 Regional Pilot Team includes:
A Core Group of nine AU/NZ Rotarians and Rotaractors. All have change-leadership credentials and meet weekly.
A Regionalisation Group elected by past, present, and future governor cohorts, providing direct representation to the project.
Five Working Groups
    Communication, Engagement, and Supporting Technologies
    Membership Experience
    New Organisation Models, Constitution, and Governance
    Public Image, Media, and Partnering
    Leadership and Development
Regionalisation District Representatives selected by each District Governor to be the conduit between the Pilot Team and the members

## Slide 6: After the Vote Sep - Jan 23 DG Geraldine
Districts continue to function as they do now.
Select and prepare some special functions (e.g. public image and communication) that can be rolled out regionally almost immediately within the interim structures.
Implement the management of the special functions regionally.
Identify at the regional and district level the 10-30 clubs that would form an area.
Determine Regional Council structure and roles.
Identify the initial Regional Support Committees.
Determine role and nature of Regional Support Teams and Area Leaders
Develop selection procedures for all leadership positions.

## Slide 7: Next six months Jan – June 23 DG Geraldine
Districts continue to function as they do now.
Select:
Regional Council members
Area Leaders
Start-up Regional Support Committees
All with maximum stakeholder involvement in the processes.
Train:
Regional Council
Area leaders
Regional Support Committees.

## Slide 8: The next Rotary Year 23-24 DG Andrea
Districts function in a condensed mode with some functions delivered by the region
District Governors and Regional Council share management and leadership with district personnel crucial to ensure continuity and support for clubs.
Establish and operationalise the Regional Council.
Establish who will be Area Leaders.
The start-up Regional Support Committees begin operation and work on regional initiatives; Area leaders begin to work with clubs.
Select additional Regional Support Committees.

## Slide 9: And the next year 24-25 DG Rob
Districts continue to exist with Governors and Regional Council sharing management and leadership with some district personnel to ensure continuity and support for clubs
The Regional Council is fully operational.
Area leaders work directly with the region and support committees with support of District Governors
COL decision on initial outcomes of regional pilot, if possible.

## Slide 10: Last year of shared government 25 - 26 DG???
Districts still exist under the stewardship of the district governor who shares management and leadership with the Regional Council.
Regional model is in full operation.
Conduct an extensive assessment of the regional model and report out to RI and all stakeholders.
Decisions on any permanent change will be the subject of decisions taken by the RI Board in accordance with the RI Constitution and Bylaws, including the requisite consultation with Districts and members at that time.